## Summary
Milestone Implementation Summary
Project | OrangeHRM demo — Directory UI (AI QA Platform validation project)
Task | orangehrm-ui-api
Workflow run | RUN-001
Workflow | default-qa-workflow v0.11.0
Summary date | 2026-10-19
Journal events read | 64 (EVT-0001 – EVT-0064); the event recording this workbook is appended after it is generated
Overall status per milestone
Order | Stage | Status | Event | Artifact version
1 | prd-generation | Approved | EVT-0007 | 1.2.0
2 | project-context | Approved | EVT-0009 | revision 1
3 | exploration | Approved | EVT-0015 | 1.1.0
4 | test-design | Approved | EVT-0037 | 1.4.0
5 | test-review | Approved | EVT-0039 | 1.3.0
6 | manual-execution | Approved | EVT-0043 | 1.2.0
7 | automation-generation | completed | EVT-0044 | 1.0.0
7 | automation-generation | completed | EVT-0045 | 1.0.0
8 | automation-execution | completed | EVT-0046 | —
8 | automation-execution | completed | EVT-0047 | —
9 | self-healing | completed | EVT-0048 | —
10 | reporting | completed | EVT-0049 | —
8 | automation-execution | completed | EVT-0050 | —
8 | automation-execution | completed | EVT-0051 | —
7 | automation-generation | completed | EVT-0052 | 1.1.0
8 | automation-execution | completed | EVT-0053 | —
7 | automation-generation | completed | EVT-0054 | 1.2.0
8 | automation-execution | completed | EVT-0055 | —
7 | automation-generation | completed | EVT-0056 | 1.3.0
8 | automation-execution | completed | EVT-0057 | —
9 | self-healing | completed | EVT-0058 | —
8 | automation-execution | completed | EVT-0059 | —
9 | self-healing | completed | EVT-0060 | —
10 | reporting | completed | EVT-0061 | —
10 | reporting | completed | EVT-0062 | —
10 | reporting | completed | EVT-0063 | —
10 | reporting | completed | EVT-0064 | —
Key counts
Test cases (TestCases.md v1.4.0) | 58
Manual execution — PASS | 40
Manual execution — FAIL | 0
Manual execution — BLOCKED | 0
Manual execution — Exploratory observed (no verdict) | 18
Bug reports (all Suspected / Open; 0 Confirmed) | 5
Cases automated (Needs Automation = TRUE: TC-054) | 1
Automation frameworks | 2
Automation runs recorded | 22 (Playwright 7: A1–A7; SHAFT 15: B1–B15)
Playwright: passed runs | 5 of 7 (A3–A7 after fixes: 5/5; latest A7 headed PASS)
SHAFT: passed runs (test PASS and build SUCCESS) | 11 of 15 (current code v1.3.0 + H-004 + H-005: B14, B15 = 2/2; latest B15 headed PASS)
Healing / fixing interventions | 6 (E-001, H-001 – H-005)
Application defects found by automation | 0
Assertions or expected results changed | 0
Autonomous / unattended healing | not demonstrated
IntelliJ IDEA execution of TC-054 | pending — not verified (no IDE result provided; no run recorded)
Original assignment deliverables
Deliverable | Path (under platform/tasks/orangehrm-ui-api/) | Status
1. Excel milestone summary | reports/MilestoneSummary.xlsx | this workbook
2. HTML workflow / sequence diagram | reports/WorkflowDiagram.html | exists
3. PRD.md | prd/PRD.md | exists
4. Exploration.md | exploration/ExplorationReport.md | exists (named ExplorationReport.md)
5. Test design CSV (Valid in Scope, Needs Automation) | test-design/TestCases.csv | exists
6. Agent execution HTML report with bug reporting | execution/ExecutionReport.html | exists
7a. Playwright automation (+ SHAFT binding) | automation/playwright-ts/, automation/shaft-java/ | exists
7b. Automation execution HTML reports | automation-execution/playwright-ts/automation-report.html, automation-execution/shaft-java/automation-report.html | exists
7c. Healing / fixing documentation | self-healing/healing-log.md | exists
Milestone 5: run via Claude and IntelliJ | automation/shaft-java/.run/TC-054 SHAFT.run.xml | Claude: done (A1–A7, B1–B15); IntelliJ: pending — not verified
All deliverables with paths: see the Deliverables sheet.

## Milestones
Milestones / stages — task orangehrm-ui-api (RUN-001)
Gated stages (1–6): the accepting approval_decision event and the approved artifact version. Stages 7–10 have no approval key: one row per stage_execution event in journal/execution-log.json.
Order | Stage | Skill version | Artifact path / runs | Artifact version | Approval key | Approval / journal event | Timestamp (UTC) | Status | Stage execution events | Source
1 | prd-generation | 1.0.1 | prd/PRD.md | 1.2.0 | PRD_APPROVED | EVT-0007 | 2026-10-15T08:43:09Z | Approved | EVT-0001, EVT-0003, EVT-0005 | journal/execution-log.json
2 | project-context | 1.1.1 | context/ProjectContext.md | revision 1 | PROJECT_CONTEXT_APPROVED | EVT-0009 | 2026-10-15T08:51:43Z | Approved | EVT-0008 | journal/execution-log.json
3 | exploration | 1.0.0 | exploration/ExplorationReport.md | 1.1.0 | EXPLORATION_APPROVED | EVT-0015 | 2026-10-15T09:54:13Z | Approved | EVT-0010, EVT-0011, EVT-0012, EVT-0014 | journal/execution-log.json
4 | test-design | 1.0.1 | test-design/TestCases.md | 1.4.0 | TEST_DESIGN_APPROVED | EVT-0037 | 2026-10-18T09:34:03Z | Approved | EVT-0016, EVT-0018, EVT-0022, EVT-0026, EVT-0034 | journal/execution-log.json
5 | test-review | 1.0.0 | test-review/TestReview.md | 1.3.0 | TEST_REVIEW_APPROVED | EVT-0039 | 2026-10-18T09:39:34Z | Approved | EVT-0020, EVT-0024, EVT-0030, EVT-0038 | journal/execution-log.json
6 | manual-execution | 1.1.0 | execution/ExecutionReport.md | 1.2.0 | MANUAL_EXECUTION_APPROVED | EVT-0043 | 2026-10-18T09:55:37Z | Approved | EVT-0027, EVT-0032, EVT-0036, EVT-0040, EVT-0042 | journal/execution-log.json
7 | automation-generation | 1.1.0 | automation/AutomationGeneration.md | 1.0.0 | none (ungated) | EVT-0044 | 2026-10-18T11:10:46Z | completed | EVT-0044 | journal/execution-log.json
7 | automation-generation | 1.1.0 | automation/AutomationGeneration.md | 1.0.0 | none (ungated) | EVT-0045 | 2026-10-18T11:10:46Z | completed | EVT-0045 | journal/execution-log.json
8 | automation-execution | n/a | runs A1–A6; automation-execution/execution-metrics.json; automation-execution/playwright-ts/automation-report.html | — | none (ungated) | EVT-0046 | 2026-10-18T11:10:46Z | completed | EVT-0046 | journal/execution-log.json
8 | automation-execution | n/a | runs B1–B6; automation-execution/execution-metrics.json; automation-execution/shaft-java/automation-report.html | — | none (ungated) | EVT-0047 | 2026-10-18T11:10:46Z | completed | EVT-0047 | journal/execution-log.json
9 | self-healing | n/a | self-healing/healing-log.md | — | none (ungated) | EVT-0048 | 2026-10-18T11:10:46Z | completed | EVT-0048 | journal/execution-log.json
10 | reporting | n/a | reports/FrameworkComparison.md; automation-execution/playwright-ts/automation-report.html; automation-execution/shaft-java/automation-report.html; reports/LearningReport.html; reports/WorkflowDiagram.html; reports/MilestoneSummary.xlsx | — | none (ungated) | EVT-0049 | 2026-10-18T11:15:22Z | completed | EVT-0049 | journal/execution-log.json
8 | automation-execution | 1.0.0 | runs A7; automation-execution/execution-metrics.json | — | none (ungated) | EVT-0050 | 2026-10-18T12:28:13Z | completed | EVT-0050 | journal/execution-log.json
8 | automation-execution | 1.0.0 | runs B7; automation-execution/execution-metrics.json | — | none (ungated) | EVT-0051 | 2026-10-18T12:28:13Z | completed | EVT-0051 | journal/execution-log.json
7 | automation-generation | 1.1.0 | automation/AutomationGeneration.md | 1.1.0 | none (ungated) | EVT-0052 | 2026-10-18T13:44:25Z | completed | EVT-0052 | journal/execution-log.json
8 | automation-execution | 1.0.0 | runs B8, B9; automation-execution/execution-metrics.json | — | none (ungated) | EVT-0053 | 2026-10-18T13:44:25Z | completed | EVT-0053 | journal/execution-log.json
7 | automation-generation | 1.1.0 | automation/AutomationGeneration.md; automation/MyBookingsAlignmentAudit.md | 1.2.0 | none (ungated) | EVT-0054 | 2026-10-18T14:14:57Z | completed | EVT-0054 | journal/execution-log.json
8 | automation-execution | 1.0.0 | runs B10, B11; automation-execution/execution-metrics.json | — | none (ungated) | EVT-0055 | 2026-10-18T14:14:57Z | completed | EVT-0055 | journal/execution-log.json
7 | automation-generation | 1.1.0 | automation/AutomationGeneration.md | 1.3.0 | none (ungated) | EVT-0056 | 2026-10-19T06:34:48Z | completed | EVT-0056 | journal/execution-log.json
8 | automation-execution | 1.0.0 | runs B12, B13, B14; automation-execution/execution-metrics.json | — | none (ungated) | EVT-0057 | 2026-10-19T06:34:48Z | completed | EVT-0057 | journal/execution-log.json
9 | self-healing | n/a | self-healing/healing-log.md | — | none (ungated) | EVT-0058 | 2026-10-19T06:34:48Z | completed | EVT-0058 | journal/execution-log.json
8 | automation-execution | 1.0.0 | runs B15; automation-execution/execution-metrics.json; automation-execution/shaft-java/automation-report.html | — | none (ungated) | EVT-0059 | 2026-10-19T07:06:09Z | completed | EVT-0059 | journal/execution-log.json
9 | self-healing | n/a | self-healing/healing-log.md | — | none (ungated) | EVT-0060 | 2026-10-19T07:06:09Z | completed | EVT-0060 | journal/execution-log.json
10 | reporting | n/a | execution/ExecutionReport.html | — | none (ungated) | EVT-0061 | 2026-10-19T08:03:54Z | completed | EVT-0061 | journal/execution-log.json
10 | reporting | n/a | automation-execution/playwright-ts/automation-report.html | — | none (ungated) | EVT-0062 | 2026-10-19T12:45:17Z | completed | EVT-0062 | journal/execution-log.json
10 | reporting | n/a | reports/WorkflowDiagram.html | — | none (ungated) | EVT-0063 | 2026-10-19T12:50:42Z | completed | EVT-0063 | journal/execution-log.json
10 | reporting | n/a | reports/FrameworkComparison.md | — | none (ungated) | EVT-0064 | 2026-10-19T12:53:30Z | completed | EVT-0064 | journal/execution-log.json

## Deliverables
Deliverable | Path | Description | Format | Status (checked on disk) | Assignment deliverable #
PRD | platform/tasks/orangehrm-ui-api/prd/PRD.md | Structured 20-section PRD (v1.2.0, PRD_APPROVED EVT-0007) | Markdown | exists | 3
Project context | platform/tasks/orangehrm-ui-api/context/ProjectContext.md | QA analysis of the approved PRD (PROJECT_CONTEXT_APPROVED EVT-0009) | Markdown | exists | —
Exploration report | platform/tasks/orangehrm-ui-api/exploration/ExplorationReport.md | Observed behavior vs ProjectContext, with evidence (v1.1.0, EVT-0015); file name differs from 'Exploration.md' | Markdown + evidence/ | exists | 4
Test cases | platform/tasks/orangehrm-ui-api/test-design/TestCases.md | 58 designed test cases (v1.4.0, TEST_DESIGN_APPROVED EVT-0037) | Markdown | exists | 5
Test cases (CSV) | platform/tasks/orangehrm-ui-api/test-design/TestCases.csv | Same 58 cases with 'valid in scope' (58 TRUE) and 'needs automation' (TC-054 TRUE) | CSV | exists | 5
Test review | platform/tasks/orangehrm-ui-api/test-review/TestReview.md | Mandatory review bound to TestCases v1.4.0 (v1.3.0, TEST_REVIEW_APPROVED EVT-0039) | Markdown | exists | 5
Agent execution report (HTML) | platform/tasks/orangehrm-ui-api/execution/ExecutionReport.html | HTML execution report with bug reporting: 40 PASS / 0 FAIL / 0 BLOCKED / 18 Exploratory observed; BUG-001 – BUG-005 Suspected (EVT-0061) | HTML | exists | 6
Execution report (Markdown) | platform/tasks/orangehrm-ui-api/execution/ExecutionReport.md | Approved source of the HTML report (v1.2.0, MANUAL_EXECUTION_APPROVED EVT-0043) | Markdown + evidence/ | exists | 6
Execution problem review | platform/tasks/orangehrm-ui-api/execution/ExecutionProblemReview.md | Review of suspected issues PR-001 – PR-008 (v1.2.0) | Markdown | exists | 6
Bug reports | platform/tasks/orangehrm-ui-api/bugs/BugReports.md | BUG-001 – BUG-005, all Suspected / Open (v1.1.0) | Markdown | exists | 6
Bug report tracker | platform/tasks/orangehrm-ui-api/bugs/BugReportTracker.xlsx | Excel tracker of BUG-001 – BUG-005 with screenshots | Excel | exists | 6
Automation project A | platform/tasks/orangehrm-ui-api/automation/playwright-ts/ | Playwright + TypeScript + Playwright Test project for TC-054 (code 1.0.0 + H-001) | Source project | exists | 7
Automation project B | platform/tasks/orangehrm-ui-api/automation/shaft-java/ | SHAFT + Selenium + Java 21 + TestNG + Maven project for TC-054 (code v1.3.0 + H-004 + H-005) | Source project | exists | 7
Automation generation report | platform/tasks/orangehrm-ui-api/automation/AutomationGeneration.md | Bindings, versions, case mapping, locators, generated-file hashes (v1.3.0) | Markdown | exists | 7
Execution metrics | platform/tasks/orangehrm-ui-api/automation-execution/execution-metrics.json | All 22 automation runs extracted from run outputs | JSON | exists | 7
Automation execution results | platform/tasks/orangehrm-ui-api/automation-execution/results/ | Per-run evidence (native reports, logs, screenshots) | Folder | exists | 7
Automation execution report — Playwright | platform/tasks/orangehrm-ui-api/automation-execution/playwright-ts/automation-report.html | Runs A1–A7; final verdict PASS (A7, headed) (EVT-0062) | HTML | exists | 7
Automation execution report — SHAFT | platform/tasks/orangehrm-ui-api/automation-execution/shaft-java/automation-report.html | Runs B1–B15; final verdict PASS (B15, headed) (EVT-0059) | HTML | exists | 7
Healing / fixing documentation | platform/tasks/orangehrm-ui-api/self-healing/healing-log.md | E-001, H-001 – H-005: reason, change, result, evidence; demonstrated vs not demonstrated | Markdown | exists | 7
Framework comparison | platform/tasks/orangehrm-ui-api/reports/FrameworkComparison.md | Part A: 2026-10-18, SHAFT code v1.0.0; Part B: later runs and current code (EVT-0064) | Markdown | exists | —
Workflow / sequence diagram | platform/tasks/orangehrm-ui-api/reports/WorkflowDiagram.html | Reusable architecture, workflow, automation sequence, TC-054 sequence (EVT-0063) | HTML | exists | 2
Learning report | platform/tasks/orangehrm-ui-api/reports/LearningReport.html | Bilingual learning report (snapshot of 2026-10-18; not updated) | HTML | exists | —
Milestone summary | platform/tasks/orangehrm-ui-api/reports/MilestoneSummary.xlsx | This workbook | Excel | exists (this file) | 1
Execution journal | platform/tasks/orangehrm-ui-api/journal/execution-log.json | Append-only journal of every significant AI action | JSON | exists | —
Prompt journal | platform/tasks/orangehrm-ui-api/journal/prompts.json | Prompts used per stage | JSON | exists | —
Workflow run | platform/tasks/orangehrm-ui-api/journal/workflow-run.json | Workflow run context (RUN-001) | JSON | exists | —
IntelliJ IDEA run of TC-054 (assignment: 'run the automation using Claude and IntelliJ') | platform/tasks/orangehrm-ui-api/automation/shaft-java/.run/TC-054 SHAFT.run.xml | Run configuration exists; no IDE execution result was provided, no run is recorded | IDE run | pending — not verified | 7

## Automation Runs
Run | Run ID | Framework | Code version | Mode | Test status | Build | Surefire | Test duration (ms) | Runner total (ms) | Wall-clock (ms) | k | N | Unfiltered count | DATA-012 pair | Error (first line)
A1 | run-20261018-A1 | Playwright TS | 1.0.0 | headless | failed | n/a (Playwright) | n/a (Playwright) | 2 | 641 | not recorded | not recorded | not recorded | not recorded | not recorded | Error: browserType.launch: Executable doesn't exist at C:\Users\QC User\AppData\Local\ms-playwright\chromium_headless_shell-1248\chrome-headless-shell-win64\chrome-headless-shell.exe
A2 | run-20261018-A2 | Playwright TS | 1.0.0 | headless | failed | n/a (Playwright) | n/a (Playwright) | 37016 | 39697 | 42089 | not recorded | not recorded | not recorded | not recorded | Error: results header shows a record count
A3 | run-20261018-A3 | Playwright TS | 1.0.0 + H-001 | headless | passed | n/a (Playwright) | n/a (Playwright) | 11169 | 12313 | 14512 | 6 | 111 | 111 | {"jobTitle":"Probation Trainee PLW1462","location":"New York Sales Office"} | —
A4 | run-20261018-A4 | Playwright TS | 1.0.0 + H-001 | headless | passed | n/a (Playwright) | n/a (Playwright) | 11494 | 12526 | 14788 | 6 | 107 | 108 | {"jobTitle":"Probation Trainee PLW1462","location":"New York Sales Office"} | —
A5 | run-20261018-A5 | Playwright TS | 1.0.0 + H-001 | headless | passed | n/a (Playwright) | n/a (Playwright) | 10036 | 11108 | 13376 | 6 | 105 | 105 | {"jobTitle":"Probation Trainee PLW1462","location":"New York Sales Office"} | —
A6 | run-20261018-A6 | Playwright TS | 1.0.0 + H-001 | headless | passed | n/a (Playwright) | n/a (Playwright) | 7647 | 8756 | 11101 | 6 | 106 | 106 | {"jobTitle":"Probation Trainee PLW1462","location":"New York Sales Office"} | —
A7 | run-20261018-A7 | Playwright TS | 1.0.0 + H-001 | headed | passed | n/a (Playwright) | n/a (Playwright) | 8252 | 12139 | 20006 | 1 | 140 | 140 | {"jobTitle":"Chief Financial Officer","location":"New York Sales Office"} | —
B1 | run-20261018-B1 | SHAFT Java | 1.0.0 | headless | not_run | FAILURE | Tests run: 0, Failures: 0, Errors: 0 | not recorded | not recorded | 23857 | not recorded | not recorded | not recorded | not recorded | Cannot invoke "String.trim()" because the return value of "java.lang.System.getProperty(String)" is null
B2 | run-20261018-B2 | SHAFT Java | 1.0.0 | headless | passed (build failed) | FAILURE | Tests run: 0, Failures: 0, Errors: 0 | 13353 | 28423 | 41848 | 6 | 111 | 111 | jobTitle="Probation Trainee PLW1462", location="New York Sales Office" | File Action "RenameFile" failed. Root cause: "java.io.FileNotFoundException: Source 'C:\Users\QC User\Desktop\FinalAI\AI-QA-Platform\platform\tasks\orangehrm-ui-api\automation\shaft-java\allure-report\index.html' does not exist"
B3 | run-20261018-B3 | SHAFT Java | 1.0.0 | headless | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 12607 | 17650 | 35135 | 6 | 110 | 111 | jobTitle="Probation Trainee PLW1462", location="New York Sales Office" | —
B4 | run-20261018-B4 | SHAFT Java | 1.0.0 | headless | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 12099 | 17004 | 32392 | 6 | 106 | 106 | jobTitle="Probation Trainee PLW1462", location="New York Sales Office" | —
B5 | run-20261018-B5 | SHAFT Java | 1.0.0 | headless | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 14903 | 19565 | 35001 | 6 | 105 | 105 | jobTitle="Probation Trainee PLW1462", location="New York Sales Office" | —
B6 | run-20261018-B6 | SHAFT Java | 1.0.0 | headless | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 12768 | 17405 | 32963 | 6 | 107 | 107 | jobTitle="Probation Trainee PLW1462", location="New York Sales Office" | —
B7 | run-20261018-B7 | SHAFT Java | 1.0.0 | headed | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 11414 | 19618 | 39573 | 1 | 140 | 140 | jobTitle="Chief Financial Officer", location="New York Sales Office" | —
B8 | run-20261018-B8 | SHAFT Java | 1.1.0 | headed | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 7439 | 33062 | 51770 | 1 | 161 | 161 | jobTitle="Chief Financial Officer", location="New York Sales Office" | —
B9 | run-20261018-B9 | SHAFT Java | 1.1.0 | headless | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 5228 | 19711 | 38616 | 1 | 8 | 8 | jobTitle="HR Manager", location="Texas R&D" | —
B10 | run-20261018-B10 | SHAFT Java | 1.2.0 | headless | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | not recorded | 24350 | 35000 | 1 | 112 | 112 | jobTitle="Chief Financial Officer", location="New York Sales Office" | —
B11 | run-20261018-B11 | SHAFT Java | 1.2.0 | headed | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 5722 | 17827 | 33000 | 1 | 113 | 114 | jobTitle="Chief Financial Officer", location="New York Sales Office" | —
B12 | run-20261019-B12 | SHAFT Java | 1.3.0 | headless | failed | FAILURE | Tests run: 1, Failures: 1, Errors: 0 | 66981 | 106875 | 142000 | not recorded | not recorded | 135 | jobTitle="HR Manager", location="Texas R&D" | Expected condition failed: waiting for element found by By.xpath: //label[normalize-space()='Location']/ancestor::div[.//div[contains(@class,'oxd-select-text-input')]][1]//div[contains(@class,'oxd-select-text-input')] to have text "Texas R&D". Current text: "-- Select --".
B13 | run-20261019-B13 | SHAFT Java | 1.3.0 + H-004 | headless | failed | FAILURE | Tests run: 1, Failures: 1, Errors: 0 | 71086 | 127486 | 156000 | 1 | not recorded | not recorded | jobTitle="HR Manager", location="Texas R&D" | Expected condition failed: waiting for element found by By.xpath: //div[contains(@class,'orangehrm-corporate-directory-sidebar')] to become invisible
B14 | run-20261019-B14 | SHAFT Java | 1.3.0 + H-004 + H-005 | headless | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 48620 | 132816 | 162000 | 1 | 140 | not recorded | jobTitle="HR Manager", location="Texas R&D" | —
B15 | run-20261019-B15 | SHAFT Java | 1.3.0 + H-004 + H-005 | headed | passed | SUCCESS | Tests run: 1, Failures: 0, Errors: 0 | 18000 | 32336 | 61000 | 1 | 178 | 178 | jobTitle="HR Manager", location="Texas R&D" | —
Code version = AutomationGeneration.md revision under test (+ fixes). Mode as recorded in the journal; A1–A6 and B1–B6 per the FrameworkComparison environment row.
B10: test duration not recorded (testng-results.xml overwritten by B11). B12–B14: demo site slow; durations not comparable. k and N for B12–B15 read from SHAFT step screenshots.
IntelliJ IDEA: no IDE run is recorded. The shared run configuration exists; the IDE execution result is pending and not verified.

## Healing
ID | Framework | Run with the failure | Classification | Root cause | Change | Verified by
E-001 | A (Playwright) | run-20261018-A1 | Environment | Playwright 1.64.1 needs Chromium build 1248; only builds 1232–1237 were installed | npx playwright install chromium (no code change) | A2 launched the browser
H-001 | A (Playwright) | run-20261018-A2 | Test-script defect (wait plumbing) | The wait regex ^\(\d+\) Records? Found$ did not allow the leading space in the header's DOM text " (111) Records Found" | Regex allows surrounding whitespace: ^\s*\(\d+\) Records? Found\s*$ | A3 PASS, then A4–A6 PASS
H-002 | B (SHAFT) | run-20261018-B1 | Framework configuration | SHAFT 10.1 TestNGListener.onExecutionStart reads system property rp.enable (ReportPortal) before its defaults exist → NPE; no test started | Surefire systemPropertyVariables: rp.enable=false (ReportPortal not used) | B2: the test ran
H-003 | B (SHAFT) | run-20261018-B2 | Environment + framework defect | SHAFT 10.1 runs its Allure CLI from <user.home>/.m2/repository/allure/… without quoting; the profile path C:\Users\QC User contains a space, so no report was generated and the final rename crashed the forked JVM (build failure; Surefire counted 0 tests although TestNG recorded the test as PASS) | Optional, empty-by-default Maven property shaft.extraArgLine appended to the test JVM argLine; on this machine -Dshaft.extraArgLine=-Duser.home=C:\Users\QCUSER~1 (8.3 short form of the same folder) | B3 BUILD SUCCESS, then B4–B6
H-004 | B (SHAFT) | run-20261019-B12 | Test-script defect (wait plumbing, introduced by the 2026-10-19 simplification) | The simplified selectOption() clicked the dropdown option without waiting for the opening list to be visible; the click on "Texas R&D" did not select it | Wait until the option is visible, then click it (Directory_Page.selectOption) | B13: both selections and Search passed (B13 then failed at H-005)
H-005 | B (SHAFT) | run-20261019-B13 | Framework configuration (introduced by the same simplification) | screenshotParams_whenToTakeAScreenshot=Always together with screenshotParams_highlightElements=true highlights each element before the action; the click on the details panel's arrow icon took 30 s and did not close the panel | screenshotParams_highlightElements=false (screenshots per action kept) | B14 PASS
Totals: 6 interventions (1 environment, 2 test-script defects, 3 framework configuration / framework defect). Application defects found: 0. Assertions or expected results changed: 0.
Every fix was made interactively by the agent after a human request and verified by a new run; autonomous / unattended healing has not been demonstrated (healing-log.md § 7).
Source: self-healing/healing-log.md § 2 (cells copied verbatim; formatting marks removed)

## Comparison
Framework comparison — measured [M] tables from reports/FrameworkComparison.md (values verbatim)
§1 Summary of the passing runs (n = 4 each) [M] — 2026-10-18, SHAFT code v1.0.0
Metric | Playwright (A3–A6) | SHAFT (B3–B6)
Pass rate after fixes | 4 / 4 | 4 / 4
Test duration — mean (min–max) | 10 087 ms (7 647–11 494) | 13 094 ms (12 099–14 903)
Runner total — mean | 11 176 ms | 17 906 ms
Wall-clock — mean | 13 444 ms | 33 873 ms
Attempts until first clean pass | 3 (1 environment, 1 script fix) | 3 (2 framework/environment fixes)
§3 Code complexity and maintainability [M] — SHAFT code v1.0.0
Measure [M] | Playwright | SHAFT
Test-code files | 6 (.ts, incl. playwright.config.ts) | 5 (.java)
Effective lines (non-blank, non-comment) | 335 | 360
Build / configuration lines | 30 (package.json, tsconfig.json) | 101 (pom.xml 69, testng.xml 12, custom.properties 20)
Direct dependencies | 3 (@playwright/test, typescript, @types/node) | 1 (SHAFT_ENGINE)
Installed footprint | 6 npm packages, 45 MB node_modules + 118 MB browser download | 342 jars, 455.6 MB on the test classpath
First build / install time | npm install 5 s (+ browser install) | first mvn test-compile 73 s (dependency download)
Caveats [M]: 4 runs per framework, alternating A/B on one machine against a shared public demo site whose data changed during the session (N moved between 105 and 111). This is an indicative measurement for one test case, not a benchmark.
§8.2 Comparable facts on the current code [M] — Playwright 1.0.0 + H-001, SHAFT v1.3.0 + H-004 + H-005 (2026-10-19)
Measure | Playwright (1.0.0 + H-001) | SHAFT (1.3.0 + H-004 + H-005)
Passing runs on the current code | A3 – A7: 5 / 5 | B14, B15: 2 / 2
Failures after the first clean pass | 0 | 2 (B12, B13): both regressions introduced by the 2026-10-19 simplification, fixed as H-004 / H-005
Fixes in total | 2 (E-001 environment, H-001 test script) | 4 (H-002 framework configuration, H-003 environment + framework defect, H-004 test script, H-005 framework configuration)
Assertions or expected results changed | 0 | 0
Headed runs | A7 | B7, B8, B11, B15
Test-code files / effective lines | 6 / 335 (unchanged) | 6 / 317 (v1.0.0: 5 / 360)
Build / configuration lines (total lines) | 31 (package.json 18, tsconfig.json 13) | 115 (pom.xml 78, testng.xml 12, custom.properties 25)
Expected-result checks | expect.soft for the five parts | TestNG SoftAssert for the five parts, then assertAll() (v1.0.0: hard asserts that stopped at the first failing part)
Test-data guards before the checks | TestDataUnavailableError when DATA-012 is missing or does not reduce the count | Hard Assert with a [TEST DATA] message for the same two conditions
Screenshots | final.png on pass; failure.png and trace.zip on failure | One screenshot per SHAFT action (23 per run in B14 / B15), element highlighting off (H-005)
Values read during the run | Logged in TC-054/steps.log (k, N, state after Reset) | Not stored; actions and locators only
Native report size per run | ~680 KB report folder (§5) | Allure single file 6.8 – 6.9 MB (B14, B15)
Run from IntelliJ IDEA | Shared run configuration exists; no IDE run recorded | Shared run configuration exists; IDE run pending, not verified
No new timing comparison: test durations are not comparable after SHAFT v1.1.0 moved login to @BeforeClass; B12–B14 ran on a slow demo site; A7 and B15 differ in day, data, clean build and screenshot policy (FrameworkComparison.md § 8.2).

## Journal Events
Event ID | Timestamp (UTC) | Event type | Stage | Skill version | Status | Approval key | Approval outcome | Trigger reason
EVT-0001 | 2026-10-14T09:23:02Z | stage_execution | prd-generation | 1.0.1 | awaiting_approval | PRD_APPROVED |  | Initial PRD generation requested (Milestone 1 only)
EVT-0002 | 2026-10-14T10:57:42Z | revision_request | prd-generation | 1.0.1 | revision_requested | PRD_APPROVED |  | Human requested changes to PRD.md
EVT-0003 | 2026-10-14T11:02:03Z | stage_execution | prd-generation | 1.0.1 | awaiting_approval | PRD_APPROVED |  | Revision after change request EVT-0002
EVT-0004 | 2026-10-14T11:26:23Z | revision_request | prd-generation | 1.0.1 | revision_requested | PRD_APPROVED |  | Human requested changes to PRD.md
EVT-0005 | 2026-10-14T11:31:01Z | stage_execution | prd-generation | 1.0.1 | awaiting_approval | PRD_APPROVED |  | Revision after change request EVT-0004
EVT-0006 | 2026-10-14T11:48:23Z | approval_decision | prd-generation | 1.0.1 | approval_not_accepted | PRD_APPROVED | not_accepted | Human replied at the PRD Generation gate
EVT-0007 | 2026-10-15T08:43:09Z | approval_decision | prd-generation | 1.0.1 | approved | PRD_APPROVED | accepted | Human replied at the PRD Generation gate
EVT-0008 | 2026-10-15T08:49:17Z | stage_execution | project-context | 1.1.1 | awaiting_approval | PROJECT_CONTEXT_APPROVED |  | Initial run requested
EVT-0009 | 2026-10-15T08:51:43Z | approval_decision | project-context | 1.1.1 | approved | PROJECT_CONTEXT_APPROVED | accepted | Human replied at the Project Context gate
EVT-0010 | 2026-10-15T08:54:38Z | stage_execution | exploration | 1.0.0 | failed | EXPLORATION_APPROVED |  | Initial exploration run requested
EVT-0011 | 2026-10-15T09:07:13Z | stage_execution | exploration | 1.0.0 | failed | EXPLORATION_APPROVED |  | Retry of exploration after EX-E13 failure in EVT-0010
EVT-0012 | 2026-10-15T09:27:09Z | stage_execution | exploration | 1.0.0 | awaiting_approval | EXPLORATION_APPROVED |  | Retry of exploration after EX-E13 failures in EVT-0010 and EVT-0011; Playwright MCP now available (session started in AI-QA-Platform/)
EVT-0013 | 2026-10-15T09:31:13Z | revision_request | exploration | 1.0.0 | revision_requested | EXPLORATION_APPROVED |  | Human requested a pre-approval review of ExplorationReport.md v1.0.0
EVT-0014 | 2026-10-15T09:34:31Z | stage_execution | exploration | 1.0.0 | awaiting_approval | EXPLORATION_APPROVED |  | Revision after review request EVT-0013
EVT-0015 | 2026-10-15T09:54:13Z | approval_decision | exploration | 1.0.0 | approved | EXPLORATION_APPROVED | accepted | Human replied at the Exploration gate
EVT-0016 | 2026-10-15T10:28:12Z | stage_execution | test-design | 1.0.1 | awaiting_approval | TEST_DESIGN_APPROVED |  | Test design requested after EXPLORATION_APPROVED (EVT-0015)
EVT-0017 | 2026-10-15T12:18:57Z | revision_request | test-design | 1.0.1 | revision_requested | TEST_DESIGN_APPROVED |  | Human decision on automation scope after manual CSV edit
EVT-0018 | 2026-10-15T12:24:05Z | stage_execution | test-design | 1.0.1 | awaiting_approval | TEST_DESIGN_APPROVED |  | Revision after change request EVT-0017 (automation scope TC-054 only)
EVT-0019 | 2026-10-15T12:27:33Z | approval_decision | test-design | 1.0.1 | approved | TEST_DESIGN_APPROVED | accepted | Human replied at the Test Design gate
EVT-0020 | 2026-10-15T12:34:46Z | stage_execution | test-review | 1.0.0 | awaiting_approval | TEST_REVIEW_APPROVED |  | Mandatory test review requested after TEST_DESIGN_APPROVED (EVT-0019)
EVT-0021 | 2026-10-15T12:38:22Z | revision_request | test-design | 1.0.1 | revision_requested | TEST_DESIGN_APPROVED |  | Human requested a test-design revision to resolve Test Review Change Required findings TR-001, TR-002, TR-003, TR-004, TR-005, TR-006, TR-007, TR-014 (TestReview.md v1.0.0, EVT-0020)
EVT-0022 | 2026-10-15T12:43:05Z | stage_execution | test-design | 1.0.1 | awaiting_approval | TEST_DESIGN_APPROVED |  | Revision after change request EVT-0021 (Test Review Change Required findings TR-001 – TR-007, TR-014)
EVT-0023 | 2026-10-15T12:44:32Z | approval_decision | test-design | 1.0.1 | approved | TEST_DESIGN_APPROVED | accepted | Human replied at the Test Design gate
EVT-0024 | 2026-10-15T12:54:10Z | stage_execution | test-review | 1.0.0 | awaiting_approval | TEST_REVIEW_APPROVED |  | Mandatory re-review after test-design revision v1.2.0 (EVT-0022) and TEST_DESIGN_APPROVED (EVT-0023)
EVT-0025 | 2026-10-15T12:55:53Z | revision_request | test-design | 1.0.1 | revision_requested | TEST_DESIGN_APPROVED |  | Human requested a test-design revision to resolve Test Review Change Required finding TR-015 only (TestReview.md v1.1.0, EVT-0024)
EVT-0026 | 2026-10-15T12:57:48Z | stage_execution | test-design | 1.0.1 | awaiting_approval | TEST_DESIGN_APPROVED |  | Revision after change request EVT-0025 (Test Review Change Required finding TR-015)
EVT-0027 | 2026-10-15T13:02:42Z | stage_execution | manual-execution | 1.1.0 | blocked |  |  | Human requested execution of TC-001 – TC-058 via Playwright MCP
EVT-0028 | 2026-10-15T13:05:03Z | approval_decision | test-design | 1.0.1 | approval_not_accepted | TEST_DESIGN_APPROVED | not_accepted | Human replied at the Test Design gate
EVT-0029 | 2026-10-15T13:06:03Z | approval_decision | test-design | 1.0.1 | approved | TEST_DESIGN_APPROVED | accepted | Human replied at the Test Design gate
EVT-0030 | 2026-10-15T13:08:42Z | stage_execution | test-review | 1.0.0 | awaiting_approval | TEST_REVIEW_APPROVED |  | Mandatory re-review after test-design revision v1.3.0 (EVT-0026) and TEST_DESIGN_APPROVED (EVT-0029); re-review requested by the human in EVT-0028
EVT-0031 | 2026-10-15T13:12:52Z | approval_decision | test-review | 1.0.0 | approved | TEST_REVIEW_APPROVED | accepted | Human replied at the Test Review gate
EVT-0032 | 2026-10-15T14:08:09Z | stage_execution | manual-execution | 1.1.0 | awaiting_approval | MANUAL_EXECUTION_APPROVED |  | Execution of TC-001 – TC-058 after TEST_REVIEW_APPROVED (EVT-0031); request recorded in EVT-0027/EVT-0028; completed after the human's Git request of the same day
EVT-0033 | 2026-10-18T09:01:03Z | revision_request | test-design | 1.0.1 | revision_requested | TEST_DESIGN_APPROVED |  | Human accepted the one-step correction of TC-024 for manual-execution test case issue TCI-002 (ExecutionReport v1.0.0, EVT-0032) and requested a test-design revision of TC-024 only
EVT-0034 | 2026-10-18T09:01:03Z | stage_execution | test-design | 1.0.1 | awaiting_approval | TEST_DESIGN_APPROVED |  | Revision after change request EVT-0033 (manual-execution test case issue TCI-002, TC-024)
EVT-0035 | 2026-10-18T09:20:18Z | revision_request | manual-execution | 1.1.0 | revision_requested | MANUAL_EXECUTION_APPROVED |  | Human instruction: write a candidate bug report for every Suspected Issue (PR-001 - PR-005), labeled Confirmed or Suspected; keep PR-006 - PR-008 separate; include the TC-024 re-check in the review notes
EVT-0036 | 2026-10-18T09:20:18Z | stage_execution | manual-execution | 1.1.0 | awaiting_approval | MANUAL_EXECUTION_APPROVED |  | Revision after request EVT-0035: candidate bug reports for PR-001 - PR-005 (all Suspected); TC-024 re-check recorded
EVT-0037 | 2026-10-18T09:34:03Z | approval_decision | test-design | 1.0.1 | approved | TEST_DESIGN_APPROVED | accepted | Human replied at the Test Design gate
EVT-0038 | 2026-10-18T09:35:36Z | stage_execution | test-review | 1.0.0 | awaiting_approval | TEST_REVIEW_APPROVED |  | Mandatory re-review (ADR-001) after test-design revision v1.4.0 (EVT-0034, TC-024 / TCI-002) and TEST_DESIGN_APPROVED (EVT-0037); the human was told before approving that approval starts this re-review
EVT-0039 | 2026-10-18T09:39:34Z | approval_decision | test-review | 1.0.0 | approved | TEST_REVIEW_APPROVED | accepted | Human replied at the Test Review gate
EVT-0040 | 2026-10-18T09:43:04Z | stage_execution | manual-execution | 1.1.0 | awaiting_approval | MANUAL_EXECUTION_APPROVED |  | Re-plan against the re-approved TestCases v1.4.0 (TEST_DESIGN_APPROVED EVT-0037) and TestReview v1.3.0 (TEST_REVIEW_APPROVED EVT-0039): re-execute TC-024, the only changed case, as announced to the human before the approvals
EVT-0041 | 2026-10-18T09:51:38Z | revision_request | manual-execution | 1.1.0 | revision_requested | MANUAL_EXECUTION_APPROVED |  | Human requested an Excel bug report tracker (3 sheets, embedded screenshots) built from BUG-001 - BUG-005 and their existing evidence, keeping all bugs Suspected and the Markdown files unchanged
EVT-0042 | 2026-10-18T09:51:38Z | stage_execution | manual-execution | 1.1.0 | awaiting_approval | MANUAL_EXECUTION_APPROVED |  | Revision after request EVT-0041: Excel bug report tracker
EVT-0043 | 2026-10-18T09:55:37Z | approval_decision | manual-execution | 1.1.0 | approved | MANUAL_EXECUTION_APPROVED | accepted | Human replied at the Manual Execution gate
EVT-0044 | 2026-10-18T11:10:46Z | stage_execution | automation-generation | 1.1.0 | completed |  |  | Human decision: implement TC-054 in two independent frameworks and compare them; this event records binding playwright-ts
EVT-0045 | 2026-10-18T11:10:46Z | stage_execution | automation-generation | 1.1.0 | completed |  |  | Human decision: implement TC-054 in two independent frameworks and compare them; this event records binding shaft-java-testng
EVT-0046 | 2026-10-18T11:10:46Z | stage_execution | automation-execution | n/a | completed |  |  | Run the generated TC-054 automation (Playwright 1.64.1 + TypeScript (Playwright Test)) against the live application
EVT-0047 | 2026-10-18T11:10:46Z | stage_execution | automation-execution | n/a | completed |  |  | Run the generated TC-054 automation (SHAFT 10.1.20260123 + Selenium 4.40.0 + Java 21 + TestNG) against the live application
EVT-0048 | 2026-10-18T11:10:46Z | stage_execution | self-healing | n/a | completed |  |  | Failures of the automation runs: classify, fix only plumbing/configuration, preserve evidence, rerun
EVT-0049 | 2026-10-18T11:15:22Z | stage_execution | reporting | n/a | completed |  |  | Produce the remaining assignment deliverables from the actual automation results
EVT-0050 | 2026-10-18T12:28:13Z | stage_execution | automation-execution | 1.0.0 | completed |  |  | Hands-on walkthrough: run TC-054 with a visible browser (headed) and inspect the results
EVT-0051 | 2026-10-18T12:28:13Z | stage_execution | automation-execution | 1.0.0 | completed |  |  | Hands-on walkthrough: run TC-054 with a visible browser (headed) and inspect the results
EVT-0052 | 2026-10-18T13:44:25Z | stage_execution | automation-generation | 1.1.0 | completed |  |  | Human request: restructure the SHAFT binding to the My Bookings framework conventions without changing TC-054 steps or assertions
EVT-0053 | 2026-10-18T13:44:25Z | stage_execution | automation-execution | 1.0.0 | completed |  |  | Verify the restructured SHAFT TC-054 (headed B8, headless B9)
EVT-0054 | 2026-10-18T14:14:57Z | stage_execution | automation-generation | 1.1.0 | completed |  |  | Human request: match the attached My Bookings code (MyBookings_TC, MyBookings_Page, BookingDetails_Page) without changing TC-054 steps, data or assertions
EVT-0055 | 2026-10-18T14:14:57Z | stage_execution | automation-execution | 1.0.0 | completed |  |  | Verify the My Bookings-aligned SHAFT TC-054 (headless B10, headed B11)
EVT-0056 | 2026-10-19T06:34:48Z | stage_execution | automation-generation | 1.1.0 | completed |  |  | Human request: simplify the SHAFT TC-054 code (basic, readable Java; no unnecessary abstractions) without changing steps, data or checks
EVT-0057 | 2026-10-19T06:34:48Z | stage_execution | automation-execution | 1.0.0 | completed |  |  | Verify the simplified SHAFT TC-054
EVT-0058 | 2026-10-19T06:34:48Z | stage_execution | self-healing | n/a | completed |  |  | Failures of runs B12 and B13 after the simplification: classify, fix only plumbing/configuration, preserve evidence, rerun
EVT-0059 | 2026-10-19T07:06:09Z | stage_execution | automation-execution | 1.0.0 | completed |  |  | Headed verification run of the approved SHAFT TC-054 code; finalize the SHAFT execution report
EVT-0060 | 2026-10-19T07:06:09Z | stage_execution | self-healing | n/a | completed |  |  | Complete the self-healing documentation: actual workflow, root causes, fixes, reruns, verification evidence, demonstrated vs not demonstrated capabilities
EVT-0061 | 2026-10-19T08:03:54Z | stage_execution | reporting | n/a | completed |  |  | Create the missing agent execution HTML report (assignment Milestone 4 / final deliverable) from the approved execution and bug-reporting artifacts
EVT-0062 | 2026-10-19T12:45:17Z | stage_execution | reporting | n/a | completed |  |  | Finalization sprint step 1: update the Playwright execution HTML report to include the existing headed run A7
EVT-0063 | 2026-10-19T12:50:42Z | stage_execution | reporting | n/a | completed |  |  | Finalization sprint step 2: update the HTML workflow/sequence diagram to the current state and explain the reusable architecture
EVT-0064 | 2026-10-19T12:53:30Z | stage_execution | reporting | n/a | completed |  |  | Finalization sprint step 3: label the original framework comparison as SHAFT code v1.0.0 and add the later runs and current-code facts